## Team Members
Team Member | Email
Peiming Chen | peiming.chen94@spsmail.cuny.edu
Genesis Middleton | genesis.middleton31@myhunter.cuny.edu
Joe Garcia | joe.garcia53@spsmail.cuny.edu
Kory Martin | kory.martin@gmail.com

## Team Artifacts
Artifact | Description
Group Folder
Group Document
Group Presentation Deck
Job Postings Data
Project Instructions & Grading Rubric

## Project Activities
Workstream | Sub Workstream | Activity | Responsible | Description | Due Date | Status | Deliverable
Foundation Setting | - | Setup Slack group | Genesis |  | 2023-03-10 | Complete
Foundation Setting | - | Setup core team documents | Kory |  | 2023-03-09 | Complete
Foundation Setting | - | Setup Google Drive | Kory |  | 2023-03-09 | Complete
Part 1 - Project Overview | - | Develop Entity Relationships for Database | Kory |  | 2023-03-11 | Complete | Entity Relationship diagram
Part 1 - Project Overview | - | Write project overview document | Kory |  | 2023-03-11 | Complete | Project Overview document
Part 1 - Project Overview | - | Share document with team for review | Kory |  | 2023-03-11 | Complete
Part 1 - Project Overview | - | Team provides edits and comments on document | All |  | 2023-03-12 | Complete
Part 1 - Project Overview | - | Submit document | Kory |  | 2023-03-12 | Complete
Part 2 - Data Analysis | Data Collection | Create spreadsheet to use for data dump | Kory |  | 2023-03-09 | Complete | Job Postings Spreadsheet
Part 2 - Data Analysis | Data Collection | Scrape assigned websites for job postings and paste into shared Google Sheet | All |  | 2023-03-14 | Not Started | Completed job posting spreadsheet
Part 2 - Data Analysis | Data Collection | Setup database and data tables in AWS | Genesis |  | 2023-03-15 | Not Started | Database setup in AWS
Part 2 - Data Analysis | - | Quick Check-in and Team Sync | All |  | 2023-03-16 | Not Started
Part 2 - Data Analysis | Data Collection | Clean data for ingestion into R | Kory |  | 2023-03-16 | Not Started | Code for cleaned R dataframe
Part 2 - Data Analysis | Data Collection | Ingest data into database using R | Joe |  | 2023-03-17 | Not Started | Code for importing cleaned R dataframe into database
| Data Analysis | Analysis of data | PeiMing |  | 2023-03-18 | Not Started | Code for analyzing data and creating data visualizations
Part 2 - Data Analysis | - | Meeting to review code/results | All |  | 2023-03-19 | Not Started
Part 2 - Data Analysis | - | Submit code | Kory |  | 2023-03-19 | Not Started | a) Publish code to GitHub b) Publish code to RPubs
Part 3 - Presentation | - | Create individual content slides | Kory, Genesis, Joe, |  | 2023-03-20 | Not Started | Complete indeividual slides
Part 3 - Presentation | - | Finalize slides | Kory / Genesis |  | 2023-03-21 | Not Started | Completed presentation deck
Part 3 - Presentation | - | Presentation Sync up | All |  | 2023-03-21 | Not Started
Part 3 - Presentation | - | Team Presentation | Kory, Genesis, Joe |  | 2023-03-22 | Not Started

## Data Tables
job_board |  | company |  | skills
id | integer | id | integer | id | integer
job_board_name | var char | company_name | var char | posting_id | integer
job_board_url | var char | company_location | var char | skill_name | var char
|  | industry | var char | skill_type | var char
posting
id | integer
company_id | integer | industry
job_board_id | integer | id | integer
title | var char | industry_name | var char
location | var char
senority_level | var char
work_type | var char
min_years_experience | integer